CHASIO BROWN  /  QUALITY ENGINEERING PORTFOLIO

QUALITY SYSTEM 02

# Jira Delivery Workflow & Handoff Model

A visible operating model for ownership, status integrity, QA/UAT handoffs, release control, and traceable evidence.

| PORTFOLIO ARTIFACT QS-02 | SCOPE Enterprise Salesforce Delivery | EDITION Sanitized / Generalized |
| --- | --- | --- |

PURPOSE Standardize how work moves through Jira so the board reflects the true delivery state, the next accountable owner, the evidence supporting each handoff, and the remaining risk.

# Operating Rules

| PRINCIPLE | WORKING RULE |
| --- | --- |
| Visible ownership | The assignee reflects the person responsible for the next active action—not the person who last touched the ticket. |
| Evidence before movement | A status change confirms its entry conditions are satisfied; required notes and evidence move with the ticket. |
| Quality starts early | QA participates in refinement, prepares while development is active, and independently assesses the completed change. |
| Business owns acceptance | QA validates functionality and risk; the authorized business/UAT owner decides operational acceptance. |
| Release is controlled | The approved candidate is promoted through staging and production with deployment, rollback, monitoring, and validation evidence. |
| Backward movement is healthy | Work returns to the responsible stage when a defect, missing requirement, data issue, or unacceptable risk is discovered. |

BOARD INTEGRITY Never move a ticket simply to make a sprint report look complete. Jira should show the true current state, owner, blocker, and residual risk.

# Recommended Story Workflow

The story record shows what was defined, built, tested, and accepted.

| # | JIRA STATUS | PRIMARY OWNER | STATUS MEANS |
| --- | --- | --- | --- |
| 1 | Draft / Intake | Business / Product / BA | Request captured and awaiting initial triage. |
| 2 | Ready for Refinement | Product / BA | Business context and draft behavior are ready for cross-functional review. |
| 3 | Ready for Sprint | Product + Delivery Team | Definition of Ready is met; item may be considered for commitment. |
| 4 | In Development | Developer | Implementation and QA preparation are active. |
| 5 | Code Review | Developer / Reviewer | Peer review, unit checks, and correction are underway. |
| 6 | Ready for QA | Assigned QA Tester | Correct build, self-test evidence, data, and handoff notes are available. |
| 7 | In QA | QA | Independent functional, regression, permission, data, and defect assessment are active. |
| 8 | QA Complete | QA | QA outcome, coverage, evidence, known issues, and residual risk are recorded. |
| 9 | Ready for UAT | Assigned UAT Tester | Business tester, scope, access, data, instructions, and QA context are confirmed. |
| 10 | In UAT | UAT Tester / Business Owner | Business users validate realistic operational workflows. |
| 11 | UAT Accepted | Business Owner | Authorized acceptance or conditional acceptance is documented. |
| 12 | Done | Product / Team | Definition of Done and required closure conditions are satisfied. |

# Exception Statuses

Blocked · QA Failed · UAT Failed · Reopened · Deferred · Cancelled · Accepted Risk

Each exception requires a reason, accountable owner, next action, and—when appropriate—a decision date or retest path.

# Handoff Control Matrix

Every responsibility change must be visible in status, assignment, and evidence.

| HANDOFF | SENDER PROVIDES | RECEIVER CONFIRMS | JIRA CHANGE |
| --- | --- | --- | --- |
| Business → Product/BA | Problem, desired outcome, urgency, users, and context. | Triage validity, scope path, priority, and owner. | Assignee = Product/BA; status = Draft / Intake |
| Product/BA → Refinement | Story, draft criteria, process/data notes, open questions. | Review from product, technical, and QA perspectives. | Status = Ready for Refinement |
| Planning → Developer | Ready criteria, sprint goal, dependencies, test owners. | Accept implementation ownership and surface blockers. | Sprint set; status = In Development; assignee = Developer |
| Developer → QA | Correct build, self-test, data/setup, version, notes, limitations. | Perform entry check; visibly accept or reject the handoff. | Status = Ready for QA; assignee = QA; handoff comment |
| QA → UAT | QA outcome, coverage, defects, evidence, build, limitations, risk. | Acknowledge scope/access/data; execute business scenarios. | Status = Ready for UAT; assignee = UAT tester |
| UAT → Release | Authorized acceptance/conditions; approved scope. | Create candidate, release controls, window, and promotion plan. | Status = UAT Accepted; release link / version set |
| Release → Operations | Exact candidate, deployment/rollback steps, smoke tests, monitoring, contacts. | Confirm window, access, observability, and response readiness. | Release status = Approved for Production / Deploying |

NO SILENT HANDOFFS Moving the card and changing the assignee are both required. The receiving owner should not need to search chat to learn which build, environment, data, scope, or limitation applies.

# Release Workflow

Use a linked release record to control promotion and production decisions across multiple approved stories.

| RELEASE STATUS | REQUIRED MEANING | PRIMARY OWNER |
| --- | --- | --- |
| Release Planning | Scope, dependencies, target window, change owners, communication, and release owner identified. | Release Lead / Product |
| Release Candidate | Approved work assembled into one identifiable candidate linked to the release. | Release / DevOps |
| Ready for Staging | Deployment, configuration, data migration, smoke, monitoring, support, and rollback plans complete. | Release Lead |
| In Staging | Candidate deployed to staging; release validation active. | Release + QA |
| Staging Complete | Results, known issues, deviations, and residual risk documented. | QA / Release |
| Release Decision | Authorized stakeholders issue Go, Conditional Go, Partial Release, No-Go, or Reschedule. | Business / Product / Release |
| Approved for Production | Window, exact version, owners, communications, monitoring, and rollback readiness confirmed. | Release Authority |
| Deploying | Approved production change in progress; logs monitored. | Release / DevOps |
| Production Validation | Safe smoke testing, monitoring, and data/integration verification active. | Operations + QA Support |
| Closed | Deployment outcome, evidence, incidents, rollback/hotfix actions, and follow-up work complete. | Release Lead / Product |

ARTIFACT INTEGRITY Promote the same approved release candidate through staging and production whenever technically possible. Any material rebuild, configuration change, or scope change requires impact review and appropriate revalidation.

# Backflow and Quality Gates

| CONDITION | TICKET ACTION | RETURN OWNER | REQUIRED RECORD |
| --- | --- | --- | --- |
| Missing / untestable requirement | Return to Ready for Refinement or mark Blocked. | Product / BA | Question, decision owner, due date, updated criteria |
| Build / handoff incomplete | Reject Ready for QA; return to development or code review. | Developer | Missing gate item and correction needed |
| QA defect | Set QA Failed / Blocked and link defect. | Developer | Reproduction, severity, evidence, build/environment |
| Environment / data issue | Use Blocked; do not automatically classify as product defect. | Environment / Data Owner | Impact, owner, workaround, expected restoration |
| UAT issue | Set UAT Failed / Reopened; classify defect vs training/policy/preference. | Product/BA + Developer | Business impact, expected behavior, disposition, retest owner |
| Staging failure | Hold candidate / issue No-Go and revalidate affected scope. | Release / Dev / QA | Failed step, candidate version, impact, correction, retest evidence |
| Production failure | Open incident and invoke rollback/hotfix criteria. | Operations / Release | Timeline, logs, decision, recovery, user/data impact |
| Accepted risk | Proceed only with written authorization. | Named Decision Owner | Risk, rationale, impact, workaround, review/target date |

# Quick Gate Checks

| GATE | CHECK |
| --- | --- |
| STORY READY | Outcome/owner clear; measurable criteria; scope boundaries; data/roles/integrations; dependencies; UAT owner; small enough to complete. |
| READY FOR QA | Peer review; correct build; dev checks; data/services; version/notes; limitations; QA assigned. |
| QA COMPLETE | Critical scenarios; regression; defects current; blocked areas disclosed; evidence; residual risk; QA outcome. |
| READY FOR UAT | UAT tester; access/data; business scenarios; QA context; known issues; decision authority; schedule. |
| RELEASE READY | UAT decision; release link; candidate identifiable; staging plan; rollback/monitoring; scope frozen; risk visible. |
| PRODUCTION COMPLETE | Deployment logs; critical smoke; integrations/jobs healthy; monitoring active; incident/rollback disposition; outcome recorded. |

PORTFOLIO SANITIZATION NOTE This portfolio edition is a generalized adaptation of an enterprise quality operating model. Institutional names, logos, internal ticket identifiers, personnel, URLs, environment names, proprietary fields, and implementation-specific details have been removed or generalized. The artifact is presented to demonstrate quality engineering method, governance, and leadership practice.